## Dev Actions
Developer actions — theoriginaltour.com
WCAG 2.2 Level AA. Every value is final — nothing is waiting on a designer. Work top to bottom; it is ordered by return. Rows 1–12 are colour values, 13–23 are markup and CSS.
Tracking: | Set column H as you go. The header row is filterable.
# | What to change | Find / current | Replace / new | Where | WCAG | Effort | Status | Note
1 | Grey text | #A3A3A3 | #767676 | Tailwind classes: text-[#A3A3A3], text-[#a3a3a3] | 1.4.3 | 1 hr | Not started | 174 elements, 31 pages. Case-insensitive find and replace. 2.52:1 -> 4.54:1. Biggest win here, no visual risk.
2 | Functional border | #e5e5e5 | #737373 | --border-primary | 1.4.11 | 30 min | Not started | 1.26:1 -> 4.74:1. Inputs and control boundaries only. Decorative dividers stay light.
3 | Strong border | #a3a3a3 | #737373 | --border-strong | 1.4.11 | 10 min | Not started | 2.52:1 -> 4.74:1.
4 | Button hover fill | #4398d4 | #2a6fa8 | --action-primary-hover | 1.4.3 | 10 min | Not started | 3.14:1 -> 5.33:1 against the white label. No label size on this site counts as WCAG large text, so all need 4.5:1.
5 | Focus ring colour | browser default black | #2a6fa8 | --focus-ring | 1.4.11 | 10 min | Not started | 2.22:1 -> 5.33:1. Applied by row 13.
6 | Focus ring, destructive buttons | #f49898 | #991b1b | --focus-ring-destructive | 1.4.11 | 10 min | Not started | 2.14:1 -> 8.31:1. Delete and cancel actions.
7 | Disabled text | #d4d4d4 | #525252 | --text-disabled | 1.4.3 | 10 min | Not started | 1.48:1 -> 5.27:1.
8 | Badge, blue | #3b82f6 | #2563eb | badge background, white label | 1.4.3 | 15 min | Not started | 3.68:1 -> 5.17:1.
9 | Badge, green | #16a34a | #15803d | badge background, white label | 1.4.3 | 15 min | Not started | 3.30:1 -> 5.02:1. Where green is an icon rather than text, leave it.
10 | Badge, pink | #ec4899 | #be185d | badge background, white label | 1.4.3 | 15 min | Not started | 3.53:1 -> 6.04:1.
11 | Badge, red label | #fce6e7 | #ffffff | label colour on the red badge | 1.4.3 | 5 min | Not started | 4.08:1 -> 4.87:1. The red background #e30910 is fine, leave it.
12 | Input field colours | no shared styles | see Note | form field styles | 1.4.11, 1.4.3 | 30 min | Not started | Border #737373 / focus ring #164291 2px outside / error border #c2070d / error text #9e1525 / placeholder #525252 / disabled #525252 on #fafafa. Field height 48px. Matches Input- Master in Figma.
13 | Focus-visible ring | no custom focus style | :focus-visible { outline: 2px solid #2a6fa8; outline-offset: 2px; } | global stylesheet | 1.4.11, 2.4.7 | 1 hr | Not started | outline-offset is required: without it the ring sits on the button at 1.77:1. Add .btn-destructive:focus-visible { outline-color: #991b1b; }
14 | Remove focus suppression | outline: none / outline: 0 / focus:outline-none | delete, or replace with the row 13 ring | grep the whole codebase | 2.4.7 | 30 min | Not started | Only remove where nothing replaces it.
15 | Skip to main content | first Tab stop is the cookie banner | <a href="#main" class="skip-link">Skip to main content</a> | every page, first element in the DOM | 2.4.1 | 1 hr | Not started | Pair with <main id="main" tabindex="-1">. CSS: position:absolute; left:-9999px; z-index:9999; and .skip-link:focus { left:8px; top:8px; }. Must sit before the cookie banner.
16 | Landmark elements | generic divs | <header role="banner"> <nav aria-label="Main"> <main id="main"> <footer role="contentinfo"> | site shell | 1.3.1 | 2 hrs | Not started | Row 15 needs this to land anywhere.
17 | Scrollers reachable by keyboard | .overflow-x-auto with no tabindex | tabindex="0" role="region" aria-label="..." | 20 regions, 14 pages | 2.1.1 | 2 hrs | Not started | Label each region for its own content, do not reuse one string.
18 | Route map text alternative | pannable map only | stop and route data as real text or a table | route map pages | 1.1.1, 2.1.1 | varies | Not started | If the stop data already exists as text on the page, this is done.
19 | Heading levels | <h3> with no <h2> above it | <h2> | 4 headings, 2 pages | 1.3.1 | 30 min | Not started | Change the tag only, keep the classes.
20 | Duplicate alt text | alt="Kensington Palace" / alt="Tower of London" | alt="" | attractions listing, 2 images | 1.1.1 | 10 min | Not started | The adjacent heading already names them.
21 | Decorative illustrations | alt text or missing attribute | alt="" | 12 illustrations | 1.1.1 | 15 min | Not started | The attribute must be PRESENT and empty. A missing alt makes screen readers announce the filename.
22 | Tap target hit areas | icon buttons below minimum | .icon-btn { min-width:44px; min-height:44px; display:grid; place-items:center; } | ~30 icon buttons and carousel arrows | 2.5.8 | 4 hrs | Not started | Grow the hit area, not the icon. No visual change.
23 | Form error markup | inspect before changing | <label for> + aria-invalid="true" + aria-describedby + role="alert" | all forms | 3.3.1, 4.1.2 | 0-4 hrs | Not started | May already be correct. Submit a form with invalid data and inspect first. Never signal an error by colour alone.
24 | Run the contrast verifier | ~214 rows flagged but unproven | node scripts/07_verify_backdrops.js | a11y-audit/local-scan | 1.4.3 | 30 min | Not started | Fix only what comes back REAL_FAIL. Do not change hero heading colours without this: the scanner could not resolve background images and wrongly flagged white text on photos. For text on imagery add a scrim, do not change the text colour.
25 | Add axe to CI | no automated gate | npx playwright test a11y.spec.ts | CI, every PR | n/a | 2 hrs | Not started | npm i -D @axe-core/playwright, fail the build on any violation. Run against a preview deploy. Pipeline is in a11y-audit/local-scan/.